## Project schedule
| CIVE 202 Project #2 | Project Members |  |  |  |  | Project start: | [7 empty] | 2026-02-23
| Group L | Michael McCarthy |  |  |  |  | Display week: | [7 empty] | 1
| SIMPLE GANTT CHART by Vertex42.com | Eddie Vargas
| https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html | Camdin McGuigan |  |  |  |  | 2026-02-23 | [6 empty] | 2026-03-02 | [6 empty] | 2026-03-09 | [6 empty] | 2026-03-16 | [6 empty] | 2026-03-23 | [6 empty] | 2026-03-30 | [6 empty] | 2026-04-06 | [6 empty] | 2026-04-13
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-02-23 to 2026-04-19
 | time axis 2026-02-23 to 2026-04-19
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Planning for function development
| Project Planning (Gantt Chart) | All members | 0% | 2026-02-23 | 2026-02-23 | 1
| Research Mix Designs | Michael McCarthy | 0% | 2026-02-24 | 2026-02-25 | 2
Draft functions in Python
| Problem #1 Translate the Excel Logic into Python | Michael McCarthy | 0% | 2026-02-25 | 2026-02-26 | 2
| Problem #2 Implement sequential User Inputs | Eddie Vargas | 0% | 2026-02-26 | 2026-02-27 | 2
| Problem #3 Generate a Final Mix Design | Camdin McGuigan | 0% | 2026-02-27 | 2026-02-28 | 2
| Problem #4 Prepare and Evaluate Four Concrete Mix Scenarios | All members | 0% | 2026-02-28 | 2026-03-01 | 2
Execution
| Data cleaning and Processing | All members | 0% | 2026-02-27 | 2026-02-28
| Testing and validation | All members | 0% | 2026-03-01 | 2026-03-02
| Written Technical Report | All members | 0% | 2026-03-03 | 2026-03-06
| Annotated Code Document (ACD) | All members | 0% | 2026-02-25 | 2026-03-02
| Scope of Work (SOW) | All members | 0% | 2026-02-26 | 2026-02-27
| Final Project integration and submission | All members | 0% | 2026-03-06 | 2026-03-07
Evaluation
| Monitor progress | All members | 0% | 2026-02-23 | 2026-03-07 | 13
| Evaluate progress | All members | 0% | 2026-03-02 | 2026-03-07 | 6
| Gather feedback | All members | 0% | 2026-03-07 | 2026-03-07 | 1
Formulas:
Display week: = [Display week:, row below]